Accreditation Steering Advisory Group

ISER Status Report Summary

As of March 2, 2022

|  |  |  |  |
| --- | --- | --- | --- |
| Section | Liaison | Status | Notes |
| Wrap-Around Sections |  |
| Table of Contents |  |  |  |
| History of College | Henny  |  |  |
| Inst Effectiveness Data | Phil  | Under Construction | Appr. 2/11th  |
| Organization of ISER | Lisa  |  |  |
| Eligibility Requirements | Henny/Lisa |  |  |
| Compliance with Commission Policies | Henny/Lisa |  |  |
| Quality Focus Essay | Lisa | Underway | Will focus on existing DEI projects in SIDE, SEA, Caring Campus, and Guided Pathways |
| Standard I |  |
| 1.A Mission | Phil | Edited | Return to Phil for updates to data that are listed throughout section; add/check evidence list |
| 1.B Quality/Effectiveness | Phil | Edited |
| 1.C Inst Integrity | Phil | Edited |
| Standard II |  |
| 2.A Instruction | Jennifer  | Edited | Collect Evidence |
| 2.B Library | Lisa/Peter | Edited | Collect Evidence |
| 2.C Student Support | Damien | Edited | Collect Evidence |
| Standard III |  |
| 3.A Human Resources | Lisa/DCHR | Edited | *Evidence mostly collected (add caring campus also)* |
| 3.B Physical Resources | Sue Royer | w/Editor | Collect Evidence |
| 3.C Technology  | Grant | Edited | Collect Evidence |
| 3.D Finance | Cathy/VPs | w/ Writing Team | Draft to Editor 3/2 |
| Standard IV |  |
| 4.A Decision-Making | Phil/Kim | Edited | Collect Evidence |
| 4.B CEO/President | Phil/Kim | Edited | *Evidence Collected* |
| 4.C Governing Board | DCAP | w/Editor | Edited the format to match new template (I.e., list of evidence moved to end of Standard) |
| 4.D Multi-College Districts | DCAP | w/Editor |